## Slide 1
Weekly Status Report
Teradata → Databricks Migration
Reporting period: 2026-10-05 to 2026-10-11 (Mon–Sun) Prepared by: Delivery Manager Date issued: 2026-10-12

## Slide 2
Executive Summary
AMBER
Overall: Amber | Change vs. last week: n/a
Reason: One open blocker on Data Migration (3 days); all other work is on track.
Highlights: Three features were delivered this week: stored procedure conversion, historical table loads and the validation test plan.
Concerns: Access to the production data source is not yet granted and has paused the next Data Migration loads.
Decisions / support needed: Approval of production source access by 2026-10-14.

## Slide 3
Milestone Progress
Workstream (Epic) | RAG | % Complete | Δ vs. last week | Points done / total | Due date | RAG reason
Schema Conversion | Green | 80% | n/a | 64 / 80 | 2026-10-30 | On track
Data Migration | Amber | 40% | n/a | 60 / 150 | 2026-11-13 | Open blocker (3 days)
Validation | Green | 15% | n/a | 12 / 80 | 2026-12-04 | On track

## Slide 4
Completed This Week
Schema Conversion: Stored procedure conversion finished and signed off (13 points).
Data Migration: Historical reference tables loaded to Databricks (8 points).
Validation: Test plan and reconciliation approach approved (5 points).

## Slide 5
Planned Next Week
Schema Conversion: Convert remaining views and complete review.
Data Migration: Resume transactional table loads once source access is approved.
Validation: Start building reconciliation scripts for migrated tables.

## Slide 6
Key Risks & Issues
# | Workstream | Risk / Issue | Days open | Impact | Mitigation plan | Owner (team)
1 | Data Migration | Production source access not granted; transactional loads paused | 3 | Med | Access request escalated to the security team; approval targeted by 2026-10-14 | Platform team

## Slide 7
Notes
Manual overrides: None
Data notes: First report in this format, so week-over-week changes and trend are not available. Figures are illustrative placeholders; replace with Jira data before issuing.